## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days |  |  |  | BIG BOLD WORDS
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  | Year | Month | Day
Start Date |  | 2017 | 10 | 23 | 2017-10-23
|  |  | Investigation | [6 empty] | 71.225
|  |  | Requirements |  |  | 25.4375 | Design |  |  | 45.7875 | Implementation | [8 empty] | 126.8375 | Release |  |  | 171.05
Team | Your team name here
|  |  | Term | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 1: 0.75; 3: 1.75; 5: 2.75; 7: 3.75; 9: 4.75; 11: 5.75; 13: 6.75; 15: 7.75; 17: 8.75; 19: 9.75; 21: 10.75
|  | Commencing | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Minimum | Expected | Stretch | Total
| Connor Waplington | PM | None | None | Minimum | Minimum | Minimum | Minimum | None | Minimum | None | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Expected | Expected | Stretch | Stretch | Stretch | Stretch |  | 50.875 | 20.175 | 60.35 | 131.4
| Ryan Charles Simms | Web Dev | None | None | Minimum | Minimum | Minimum | Minimum | None | Minimum | None | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Expected | Stretch | Stretch | Stretch | Stretch |  | 55.9625 | 10.0875 | 60.35 | 126.4
| Alvaro Alamillo Vargas Real Jimenez | TL | None | None | None | Minimum | Minimum | Minimum | None | Minimum | None | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Expected | Expected | Expected | Stretch | Stretch |  | 50.875 | 30.2625 | 30.175 | 111.3125
| Syed | Design | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Muhammed | Design | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| John | Programmer | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Member 7 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Member 8 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Member 9 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Member 10 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Hours | Minimum | 0 | 0 | 10.175 | 15.2625 | 15.2625 | 15.2625 | 0 | 15.2625 | 0 | 0 | 0 | 15.2625 | 15.2625 | 15.2625 | 15.2625 | 15.2625 | 10.175 | 0 | 0 | 0 | 0 | 0
|  | Expected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0875 | 30.2625 | 10.0875 | 10.0875 | 0 | 0 | Totals | 157.7125 | 60.525 | 150.875 | 369.1125 | Hours
|  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.175 | 30.175 | 45.2625 | 45.2625
| Total Hours | Week | 0 | 0 | 10.175 | 15.2625 | 15.2625 | 15.2625 | 0 | 15.2625 | 0 | 0 | 0 | 15.2625 | 15.2625 | 15.2625 | 15.2625 | 15.2625 | 20.2625 | 30.2625 | 40.2625 | 40.2625 | 45.2625 | 45.2625 | Total |  |  | 369.1125 |  | Hours
| Total Hours | Sprint | 2017-10-30: 0; 2017-11-13: 25.4375; 2017-11-27: 30.525; 2017-12-11: 15.2625; 2017-12-25: 0; 2018-01-08: 15.2625; 2018-01-22: 30.525; 2018-02-05: 30.525; 2018-02-19: 50.525; 2018-03-05: 80.525; 2018-03-19: 90.525 | Total |  |  | 369.1125 |  | Hours
You have | 369.1125 | Hours, to spend on your project